## Incidents
SIBS Ref. | Description | Open Date | Opened By | Request Type | Closed Date | Afected Cards | Days to Resolve | Comments
27042017-000687 | Media Markt cards marked as sent to customer 06/04, sent only 12/04 | 2017-04-11 | Inês Emilio | Incident | 2017-04-13 | 400 | 3 | File 20170403002, 04-04-2017, 06945
27042017-000687 | Provisory cards from RP Braga sent to RP Guarda and vice-versa | 2017-04-18 | Iva Silva | Incident | 2017-04-21 | RP Braga - 200; RP Guarda - 250 | 4
03052017-000689 | Provisory cards produced with chip EMV | 2017-05-03 | Sofia Oliveira | Incident | 2017-05-15 | 12 | 9 | Affected cards were re-produced and sent to the partner shop.
Formulas:
Days to Resolve = IF([Closed Date]<>"",NETWORKDAYS([Open Date],[Closed Date]),"")